## Product Backlog
PRODUCT BACKLOG
ID | Story/Feature/Request/Bug… | Category | Priority | Resposibility | Duration (hrs) | Duration %
6 | Initialiser carte | Carte | 1 | H/J/C | 8 | 22.86%
2 | Communication PC/Carte | Réseau | 2 | GN | 8 | 22.86%
1 | Créer projet GitHub | GitHub | 3 | GN/GC/C | 1 | 2.857%
3 | Morse | Développement | 4 | H/J/C | 8 | 22.86%
4 | Cryptage | Développement | 5 | GC/GN/C | 2 | 5.714%
5 | Communication PC/Carte/Carte/PC | Réseau | 6 | GN | 8 | 22.86%
Totals |  |  |  |  | 35 | 100%
Note on C7: Auteur: An ID should not be changed once it has been assigned
Note on D7: Auteur: Description of the work package. Should be concise but understandable!
Note on E7: Auteur: Category of the work package (e.g. Interface, Design, AI, …)
Note on F7: Auteur: Priority = Value / Cost
Note on G7: Auteur: Who is responsible for this work package?
Note on H7: Auteur: Estimation of effort for this work package (story points or ideal days)
Note on I7: Auteur: Percental effort

## Alpha-Sprint
SPRINT 1 - Alpha
GOAL
Milestone Alpha Version
[6 empty] | KW19 | [6 empty] | KW20 | [6 empty] | KW21
Sprint No | Story ID | Task No | Topic / Activity |  | Effort | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
|  |  |  | Resposibility | Remaining | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So
[5 empty] | 9.25 | 9.25 | 9.25 | 8 | 8 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1
1 | 1 | 1 | Créer projet GitHub | GN | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 2 | Envoyer un message texte à la carte | GN | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 3 | Transformer un message texte en Morse | GC | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
|  | 4 | Faire clignoter la LED | H/J | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Move to beta sprint
Note on G35: Auteur: Total effort (how much work is left to do in this sprint?)
Note on H35: Auteur: Total effort (this number should decrease by time)
Note on G36: Auteur: The effort for every task is estimated and noted down here, should not exceed 8 hours.

## Beta-Sprint
SPRINT 2 - Beta
GOAL
Milestone Beta Version
[6 empty] | MAI | [6 empty] | JUNI
[6 empty] | KW22 | [6 empty] | KW25 | [6 empty] | KW26 | [6 empty] | KW27
Sprint No | Story ID | Task No | Topic / Activity |  | Effort | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
|  |  |  | Resposibility | Remaining | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So
[5 empty] | 13.75 | 13.75 | 13.75 | 11.75 | 11.75 | 11.75 | 11.25 | 8.25 | 8.25 | 7.25 | 7.25 | 7.25 | 7.25 | 6.25 | 6.25 | 5.25 | 5.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 1
2 | 1 | 1 | Configurer Autotools | GC | 1 | bar: Mo to So
| 2 | 2 | Recevoir un message texte avec la carte | GN | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 3 | Faire clignoter la LED (Test) | H/J/C | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 4 | Crypter un message (CESAR) | GC/GN | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5 | Décrypter un message (CESAR) | GC/GN | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 6 | Télécharger BSP | H/J/C | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 7 | Compiler BSP | H/J/C | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0
|  | 8 | Flasher carte | H/J/C | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0
Move to complete sprint
Note on G35: Auteur: Total effort (how much work is left to do in this sprint?)
Note on H35: Auteur: Total effort (this number should decrease by time)

## Completion
SPRINT 2 | 3 - Completion
GOAL
Milestone Final Version
[6 empty] | JUNI | [6 empty] | JULI
[6 empty] | KW28 | [6 empty] | KW29 | [6 empty] | KW30 | [6 empty] | KW30
Sprint No | Story ID | Task No | Topic / Activity |  | Effort | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
|  |  |  | Resposibility | Remaining | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So | Mo | Di | Mi | Do | Fr | Sa | So
[5 empty] | 10.5 | 10.5 | 10.5 | 9.5 | 9.5 | 9.5 | 9.5 | 8.5 | 8.5 | 8.5 | 7.5 | 7.5 | 7.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 4.5 | 4.5 | 4 | 4 | 2 | 2
3 | 1 | 1 | Rédiger Readme | GC/C | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
| 2,3,4 | 2 | Faire fonctionner morse/cryptage et communication ensemble | GC/GN/C/H/J | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| 5 | 3 | Faire un réseau PC/Carte/Carte/PC | GN | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | 4 | Rendre la communication bidirectionnelle | GN | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 5 | Boot server au démarrage carte | H/J | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0
Canceled
Note on G35: Auteur: Total effort (how much work is left to do in this sprint?)
Note on H35: Auteur: Total effort (this number should decrease by time)